# Multiview Radiographic Fracture Detection with Correct Anatomic Naming

Research proposal — Detroit Medical Center / Wayne State University

Gregory Schwing, MD, PhD — Department of Surgery

September 2026

# Summary

Commercial AI already tells a radiologist that a bone is broken, and does it well enough to be running in hundreds of hospitals. What it does not do is say which bone, in a way that survives anatomic variation, or outline the fracture, or characterize it.

This proposal builds a multiview model that produces a structured finding rather than a flag — detection, an outline of the fracture, the named bone or level with side, and whether the fragment is displaced — across the structures a trauma series covers: vertebrae, sacrum, pelvis and hips, ribs, and proximal femur. It is trained on public data, refined on DMC imaging, and is research only: no output enters the medical record and no clinician sees it during care.

# What the system would output

For every radiograph, per finding:

| Output | Form | Why it is not already available |
| --- | --- | --- |
| Fracture present | probability | Solved commercially; included as the baseline |
| Fracture outline | pixel mask | Cleared products localize with a box, not a boundary |
| Bone / level name | label + side | The failure mode this project exists to fix |
| Displacement | none / minimal / displaced | Not offered by cleared products; drives management |
| Spinopelvic parameters | PI, PT, SS, LL, PI–LL | Available separately, not alongside the fracture read |
| Anatomic anomaly | L6, lumbar rib, transitional | Not offered anywhere |

# Prior art, and what hospitals are actually running

Detection is a commercial product. GLEAMER’s BoneView received FDA 510(k) clearance in March 2022 for detection and localization of fractures across the appendicular skeleton, rib cage, and thoracic and lumbar spine. It is deployed in more than 300 institutions across 13 countries, is used by over 3,500 radiologists and emergency physicians, and is distributed through Aidoc, Fujifilm, Ferrum Health and Blackford. Reported effects are a 10.4-point gain in fracture-detection sensitivity, a 29% reduction in false negatives, and a 15% reduction in reading time.1 Competing detection work reports external-validation AUC of 0.90 (95% CI 0.84–0.95) for vertebral compression fracture on radiographs.2

Spinopelvic measurement is also solved. A 2025 meta-analysis of 15 studies and more than 10,000 radiographs reports pooled mean absolute error of 4.1° for pelvic incidence, ICC above 0.81 against human measurement.3

Three things remain open, and they are the proposal.

Naming. A detector reporting a fracture at “L1” is counting, and the count fails where it matters. Lumbosacral transitional vertebrae occur in 4–30% of people depending on definition,4 the accepted standard for numeration is whole-spine imaging counted caudally from C25 — which a trauma film cannot provide — and wrong-level spine surgery runs at roughly one in 3,110 procedures with transitional anatomy the usual cause.6 The ambiguity is specific: four rib-free lumbar vertebrae may mean an L1 bearing a lumbar rib or an L5 assimilated to the sacrum; six may mean a true sixth lumbar vertebra or a T12 with aplastic ribs. The observation is identical within each pair. The same counting problem applies to ribs, and side is routinely mislabeled — quality control on our own CT corpus caught four records carrying a left hip on the patient’s right.

Outlining. Cleared products draw a box. A boundary is what supports measurement — fragment size, angulation, displacement distance.

Characterization. Displacement is what changes management, and no cleared product reports it.

What we already hold. CTSpinoPelvic1K is an openly licensed release of 802 CT records placing spine, sacrum, hips, femora and per-level ribs on one coordinate frame, with explicit classes for a sixth lumbar vertebra, a thirteenth thoracic vertebra, a separately carved first sacral segment, and lumbar ribs.7 It was built to test whether local morphology alone can name a structure without the global count, and it ships per-level morphometry and validated spinopelvic parameters.

# Public data available for pretraining

No DMC data is needed to build the first working model. The following are openly available and cover the three outputs above:

| Dataset | Size | What it supplies |
| --- | --- | --- |
| FracAtlas8 | 4,083 radiographs | Fracture segmentation masks — the outline task |
| GRAZPEDWRI-DX | 20,327 images, 6,091 patients | 67,771 annotated objects: fractures, implants, boxes and polygons |
| VinDr-SpineXR | 10,469 spine radiographs | Lesion boxes, 13 categories — spine-specific |
| VinDr-RibCXR | chest radiographs | Individual rib segmentation and labeling |
| MURA | 40,561 radiographs | Large-scale normal/abnormal pretraining (no localization) |
| RSNA Cervical Spine Fracture | CT | Fracture supervision in 3D |
| CTSpinoPelvic1K7 | 802 CT | Correct level, rib number and side under variant anatomy |

The gap none of them fill is the pairing of a radiograph with a correct anatomic name under transitional anatomy — which is why the CT corpus matters: digitally reconstructed radiographs generated from it carry labels that are already correct, supervision unobtainable from radiographs alone, because on a radiograph the correct name is precisely what is unknown.

# What needs to be done

Stage 1 — Public-data model (no DMC data, no approvals needed). Train detection and outline heads on FracAtlas and GRAZPEDWRI-DX; the naming head on DRRs from CTSpinoPelvic1K plus VinDr-RibCXR; the parameter head on the existing CT-derived measurements. Deliverable: a model with published-benchmark performance, built entirely on public data.

Stage 2 — DMC refinement (research use only). A retrospective, de-identified cohort of DMC trauma radiographs with paired CT from the same encounter. CT settles both fracture and name and becomes the reference standard. Fine-tune for local scanner, protocol and population.

Stage 3 — Validation and evaluation. Held-out DMC cases never used in training, reported in the terms decisions are made in: sensitivity for injuries missed on the initial film and found on subsequent CT; naming accuracy against CT, stratified into ordinary and transitional anatomy, since aggregate accuracy hides failure in exactly the 4–30% where the question is hard; outline agreement (Dice) against CT-derived fracture extent; displacement against the dictated report; spinopelvic parameters against the published error bands.3

Scope note: the CT corpus reaches the axial skeleton, hips and proximal femur. Long bones below the femur would need a separate imaging source and are a later extension.

# Regulatory and institutional pathway

This is research, not clinical use, and the distinction is deliberate. All analysis is retrospective on completed encounters. No output is placed in the medical record, returned to a treating clinician, or used in any care decision. A model used this way is not a medical device; prospective use at the point of care would be, and is explicitly out of scope.

IRB — this study requires approval, and that is not the pathway our existing work used. The CTSpinoPelvic1K dataset work received a Non-Human Participant Research determination (WSU IRB HPR 2026-269, 2 September 2026) because it is built entirely from publicly released, already de-identified imaging; that letter itself notes that changes to the study plan may affect the determination. This proposal is categorically different: it draws imaging and reports from DMC patients’ own records, which is human subjects research and requires IRB review and approval. That the data is de-identified before analysis does not change it, because assembling the cohort requires reaching identifiers in the first place.

A full protocol will therefore be submitted to the WSU IRB (irb.wayne.edu, 313-577-1628). Retrospective review of records collected for clinical purposes is commonly eligible for expedited review, and studies of this design commonly request a waiver of informed consent and a HIPAA waiver of authorization — but the review category and the waivers are the IRB’s determination to make, and are named here as what will be requested rather than what applies. De-identification and DICOM header scrubbing occur under the approved protocol, before any imaging is used for model development.

Two approvals, not one. The determination letter for our existing work states that projects must obtain support from any unaffiliated institution involved, and names DMC among the applicable affiliates. DMC authorization is therefore a separate approval from Wayne State’s, and both are needed before imaging moves. The same letter notes that work touching identifiable PHI must adhere to HIPAA regardless of the human-participant question and may require authorization from the covered entity’s privacy officer.

AI platform authorization — the step most people miss. The determination letter issued for our existing dataset work carries a condition that will apply here too and is easy to overlook: “for the use of AI platforms in research, please consult with C&IT regarding authorization to use external software.” The route is the Academic Research Technology team at services@wayne.edu. This is worth resolving early, and it argues for training on WSU-managed compute rather than commercial cloud or external model APIs — doing so keeps the data inside the institution and avoids the external-software authorization question entirely.

# Data handling and computing environment

Nothing leaves Wayne State. All imaging is stored on WSU-managed research storage and processed on the WSU high-performance computing cluster (the Grid). No patient imaging is copied to personal machines, personal cloud accounts, commercial cloud compute, or any third-party model or inference API. Models are open-weight and trained locally, so there is no external software to authorize under the determination letter’s AI-platform condition — the condition is answered by not using one. Academic Research Technology (services@wayne.edu) will be consulted before any tool outside that boundary is added.

What is already in place. The investigator holds an active Grid account with roughly 5 TB of allocated storage and access to NVIDIA H200 NVL GPU nodes under SLURM, on which the CTSpinoPelvic1K pipeline already runs. Stage 1 needs nothing further.

What will be requested, and from where. C&IT’s Research Technology service catalog (services.wayne.edu → Research technology) is the single intake for the resources this project needs:

| Service | Used for | What WSU documents |
| --- | --- | --- |
| High performance computing | GPU training; existing account | No cost; any WSU faculty, staff or student with an AccessID and a research task; new accounts within two business days; allocation first come, first served |
| Research storage request | A group directory for the DMC cohort, sized to the cohort | Quota checked with wsuquota; additional space requested in GB; Panasas tiers, Tier 1 backed up for two weeks |
| Research consulting | Confirming the storage tier and any control needed for the cohort | Advisory; also the stated route for grant-support questions |
| Research data request | If DMC imaging is delivered through a WSU broker rather than directly | Form-based |

The catalog states no lead times beyond account creation, so the storage request will be filed as soon as the cohort size is known rather than when the imaging is ready to move.

The one thing WSU does not document, and how the design makes it moot. No public WSU page states whether identifiable PHI may be placed on the Grid; the Confidential Information Policy (07-2) classifies PHI and personal information collected under IRB-approved protocols as confidential data with access limited to those whose duties require it, but does not name approved systems. Rather than rely on an answer, the workflow is arranged so the question does not arise: de-identification and DICOM header scrubbing occur before any imaging reaches the Grid. Only de-identified imaging is stored or processed on the cluster. Any linkage between study identifiers and the medical record, if one is retained at all, stays within the DMC environment under the approved protocol and is not needed for model development. The permitted-systems question will still be put to hpc@wayne.edu and the Information Security Office before the first transfer, so that the answer is on record.

Two stages, different exposure. Stage 1 uses only public datasets and digitally reconstructed radiographs from an already-published, de-identified CT release — no PHI, so the model is built and benchmarked before any DMC data is requested. Only Stages 2 and 3 touch institutional imaging, and only in de-identified form.

Access, retention and publication. Access to the study directory is limited to named study personnel. Retention and destruction follow the approved protocol and institutional policy. What is published is trained model weights and aggregate performance figures, not imaging; any figure showing a radiograph would use a public-dataset case or require separate authorization.

# What is being asked

- Access to a retrospective DMC trauma imaging cohort — paired radiographs and CT from the same encounter — under an approved IRB protocol.

- Clinical framing and endpoint selection: which outputs would change a decision, and at what operating point a missed injury is worse than a false alarm.

- Co-investigator standing, and guidance on where such a tool could eventually fit if the research phase justified a clinical evaluation.

Radiological adjudication is covered by two radiology collaborators supporting the existing dataset work; no reading burden falls on the trauma service.

[Cohort size, date range, scope, effort and authorship to be discussed.]

# References

- GLEAMER BoneView: FDA 510(k) clearance, March 2022; deployment and reader-study figures as reported by the manufacturer and trade press. https://www.gleamer.ai

- Zhang H, Xu R, Guo X, et al. Deep learning-based automated high-accuracy location and identification of fresh vertebral compression fractures from spinal radiographs: a multicenter cohort study. Front Bioeng Biotechnol. 2024;12:1397003. doi:10.3389/fbioe.2024.1397003

- Glaser D, AlMekkawi AK, Caruso JP, et al. Deep learning for automated spinopelvic parameter measurement from radiographs: a meta-analysis. Artif Intell Surg. 2025;5:1–15. doi:10.20517/ais.2024.36

- Konin GP, Walz DM. Lumbosacral transitional vertebrae: classification, imaging findings, and clinical relevance. AJNR Am J Neuroradiol. 2010;31(10):1778–1786. doi:10.3174/ajnr.A2036

- Lian J, Levine N, Cho W. A review of lumbosacral transitional vertebrae and associated vertebral numeration. Eur Spine J. 2018;27(5):995–1004. doi:10.1007/s00586-018-5554-8

- Epstein NE. A perspective on wrong level, wrong side, and wrong site spine surgery. Surg Neurol Int. 2021;12:286. doi:10.25259/SNI_402_2021

- Schwing G, et al. CTSpinoPelvic1K: spine, pelvis, ribs and femora in one coordinate frame, annotated for lumbosacral transitional anatomy. Zenodo. doi:10.5281/zenodo.22139642 (concept; v7 at doi:10.5281/zenodo.22242745). Dataset descriptor in preparation.

- Abedeen I, Rahman MA, Prottyasha FZ, et al. FracAtlas: a dataset for fracture classification, localization and segmentation of musculoskeletal radiographs. Sci Data. 2023;10:521. doi:10.1038/s41597-023-02432-4